## Risks
Readably Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2020-04-18 | Poor Database Security | Database of the project lacks of security. | D | 5 | 10% | 0.5 | Technology | Improve security and notify the customers about the breach.
2 | 2020-04-18 | Poor Payment Security | Third-party payment gateways lack of security. | D | 5 | 10% | 0.5 | Technology | Improve security, notify the customer about the breach and repay the money to the customer or give compensation.
3 | 2020-04-18 | Poor Web Application Security | Components of the application makes the application more vulnerable to the security attacks. | D | 4 | 30% | 1.2 | Tools | Improve and do a reassessment of the application security, notify the customer about the breach if the breach level is critical.
4 | 2020-04-18 | Database Crash | Database crashes unexpectedly. | D | 5 | 10% | 0.5 | Tools | Recover the data from the database, find the cause of crash and fix.
5 | 2020-04-18 | Third-Party Application Unavailable | Unavailability of the integration. | D | 5 | 10% | 0.5 | Technology | Contact the third-party and integrate a new third-party application.
6 | 2020-04-18 | Third-Party Application Security Breach | Poor security of the integrated application. | D | 5 | 20% | 1 | Technology | Notify the customers about the breach, request a reassessment from the third-party application and integrate a new third-party application if needed.
7 | 2020-04-18 | Server Connection Failure | The connection between the application and the server goes off. | D | 5 | 10% | 0.5 | Tools | Find the cause and fix.
8 | 2020-04-18 | Server Response Failure | Servers does not respond or does not process necessary actions. | D | 5 | 10% | 0.5 | Tools | Find the cause and fix.
9 | 2020-04-18 | Requirements Change | There can be nore changes to the requirements than anticipated. | I | 3 | 20% | 0.6 | Requirements | Derive traceability information to assess requirements change impact; maximize information hiding in the design.
10 | 2020-04-18 | Third-Party Application Misconfiguration | Misconfiguration of the integration. | D | 5 | 10% | 0.5 | Technology | Reconfigure the third-party application.
11 | 2020-04-18 | Underestimated Complexity | Underestimation of the project complexity. | D | 3 | 50% | 1.5 | Tools | Replan the project, hire more staff, request more resource from the management.
12 | 2020-04-18 | Lack of Used Technologies Knowledge of A Project Member | Team member cannot use the programs or frameworks used to make the project. | D | 4 | 30% | 1.2 | People | Held a meeting to teach the technologies.
13 | 2020-04-18 | Staff Illnes | Project member having a health problem. | D | 3 | 40% | 1.2 | People | Reorganize team so that there is more overlap of work and people therefore understand each other’s jobs.
14 | 2020-04-18 | Underestimated Development Time | Underestimation of the time to finish the project. | D | 3 | 50% | 1.5 | Tools | Investigate buying-in components; investigate use of a program generator.
15 | 2020-04-18 | Withdrawal from The Project Team | A team member is left the team. | D | 3 | 10% | 0.3 | People | Management should recruit a new team member.
16 | 2020-04-18 | Product Competition | A similar web application can be more popular. | I | 2 | 100% | 2 | Business | More aggressive marketing, low cuts from stores, implementing new features.
17 | 2020-04-18 | Unsatisfied Customers | Customers don't like the application or the application is not popular. | I | 5 | 20% | 1 | Business | Adding more features, books, product types, more promotion and discount.
18 | 2020-04-18 | Defective Components | A component of the project is unreliable. | D | 5 | 10% | 0.5 | Technology | Replace potentially defective components with bought-in components of known reliability.